## Schedule
| 2008 |  |  | July | [8 empty] | August | [30 empty] | September | [29 empty] | October
|  |  |  | w | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
|  |  |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
FIELD DEPLOYMENT SCHEDULE
Trip number | Local or International | T-PARC / Monterey CA | Days on the field
1 | L | Ops Director (Moore) | 38 | bar: July T 24 to August S 30
1 | L | Ops Director (Dirks) | 36 | bar: August T 26 to September T 30
1 | L | Project Mgr (Salazar) | 7 | bar: July W 30 to August T 5
1 | L | SE Displays (Burghart) | 16 | bar: July M 28 to August T 12
1 | L | AS Field Catalog (Stossm) | 18 | bar: July S 26 to August T 12
1 | L | SE (VanAndel) support in Monterey | 18 | August M 11: JVA; August T 12: JVA; August W 13: JVA; August T 14: JVA; August F 15: JVA; August S 16: JVA; August S 17: JVA; August M 18: JVA; August T 19: JVA; August W 20: JVA; August T 21: JVA; August F 22: JVA; August S 23: JVA; August S 24: JVA; August M 25: JVA; August T 26: JVA; August W 27: JVA; August T 28: JVA
1 | L | Data support (Young) | bar: August S 17 to August T 21
T-PARC / GUAM / RAF
1 | I | Tech #1 (Cowan) | 17 | August T 5: T#1; August W 6: T#1; August T 7: T#1; August F 8: T#1; August S 9: T#1; August S 10: T#1; August M 11: T#1; August T 12: T#1; August W 13: T#1; August T 14: T#1; August F 15: T#1; August S 16: T#1; August S 17: T#1; August M 18: T#1; August T 19: T#1; August W 20: T#1; August T 21: T#1
1 | I | Tech #2 (Ta) | 17 | August T 5: T#2; August W 6: T#2; August T 7: T#2; August F 8: T#2; August S 9: T#2; August S 10: T#2; August M 11: T#2; August T 12: T#2; August W 13: T#2; August T 14: T#2; August F 15: T#2; August S 16: T#2; August S 17: T#2; August M 18: T#2; August T 19: T#2; August W 20: T#2; August T 21: T#2
1 | I | Tech #3 (Irwin) | 23 | August W 20: T#3; August T 21: T#3; August F 22: T#3; August S 23: T#3; August S 24: T#3; August M 25: T#3; August T 26: T#3; August W 27: T#3; August T 28: T#3; August F 29: T#3; August S 30: T#3; August S 31: T#3; September M 1: T#3; September T 2: T#3; September W 3: T#3; September T 4: T#3; September F 5: T#3; September S 6: T#3; September S 7: T#3; September M 8: T#3; September T 9: T#3; September W 10: T#3; September T 11: T#3
1 | I | Tech #4 (Bruning) | 23 | August W 20: T#4; August T 21: T#4; August F 22: T#4; August S 23: T#4; August S 24: T#4; August M 25: T#4; August T 26: T#4; August W 27: T#4; August T 28: T#4; August F 29: T#4; August S 30: T#4; August S 31: T#4; September M 1: T#4; September T 2: T#4; September W 3: T#4; September T 4: T#4; September F 5: T#4; September S 6: T#4; September S 7: T#4; September M 8: T#4; September T 9: T#4; September W 10: T#4; September T 11: T#4
1 | I | Tech #5 (Murphy) | 24 | September W 10: T#5; September T 11: T#5; September F 12: T#5; September S 13: T#5; September S 14: T#5; September M 15: T#5; September T 16: T#5; September W 17: T#5; September T 18: T#5; September F 19: T#5; September S 20: T#5; September S 21: T#5; September M 22: T#5; September T 23: T#5; September W 24: T#5; September T 25: T#5; September F 26: T#5; September S 27: T#5; September S 28: T#5; September M 29: T#5; September T 30: T#5; October W 1: T#5; October T 2: T#5; October F 3: T#5
1 | I | Tech #6 (Bruning) | 24 | September W 10: T#6; September T 11: T#6; September F 12: T#6; September S 13: T#6; September S 14: T#6; September M 15: T#6; September T 16: T#6; September W 17: T#6; September T 18: T#6; September F 19: T#6; September S 20: T#6; September S 21: T#6; September M 22: T#6; September T 23: T#6; September W 24: T#6; September T 25: T#6; September F 26: T#6; September S 27: T#6; September S 28: T#6; September M 29: T#6; September T 30: T#6; October W 1: T#6; October T 2: T#6; October F 3: T#6
T-PARC / GUAM/ DROP
1 | I | Master Tech Drop (Korn) | 57 | bar: August W 6 to October W 1
1 | I | Tech Drop (K. Spowart) | 18 | bar: August W 6 to August S 23
1 | I | Tech Drop (L. Tudor) | 28 | bar: August T 19 to September M 15
1 | I | Tech Drop (C. Golubieski | bar: September F 12 to October T 2
PROJECT MANAGERS
1 | I | Project Mgr (Meitin) | 34 | bar: July T 24 to August T 26
1 | I | Project Mgr (Baeuerle) | 25 | bar: August S 23 to September T 16
1 | I | Project Mgr (RAF-Jensen) | 24 | bar: September W 10 to October F 3
SA and SE's
1 | I | SA1 (Russ) | 28 | bar: July T 24 to August W 20
1 | I | SA2 (Ling) | 48 | bar: July T 24 to August S 9; September T 2 to October T 2
1 | I | SA3 (Vinson) | 26 | bar: August S 16 to September T 9
1 | I | SE (Martin) | 20 | bar: August T 7 to August T 26
T-PARC / ELDORA
1 | I | Eng #1 (Loew) | 22 | bar: August T 7 to August T 28
1 | I | Tech 1 (Gales) | 33 | bar: August W 6 to September S 7
1 | I | Tech 2 (Strong) | 28 | bar: August T 7 to September W 3
1 | I | Eng #2 (Spowart) | 25 | August S 23: MPS; August S 24: MPS; August M 25: MPS; August T 26: MPS; August W 27: MPS; August T 28: MPS; August F 29: MPS; August S 30: MPS; August S 31: MPS; September M 1: MPS; September T 2: MPS; September W 3: MPS; September T 4: MPS; September F 5: MPS; September S 6: MPS; September S 7: MPS; September M 8: MPS; September T 9: MPS; September W 10: MPS; September T 11: MPS; September F 12: MPS; September S 13: MPS; September S 14: MPS; September M 15: MPS; September T 16: MPS
1 | I | Eng #3 (Phinney) | 20 | bar: September S 13 to October T 2
1 | I | Tech 3 (Emmett) | 34 | bar: August S 30 to October T 2
1 | I | Tech 4 (Holden) | 31 | bar: September T 2 to October T 2
2 | I | ELDORA lead Sci (WCLee) | 54 | bar: August W 6 to September S 6; September T 11 to October T 2
2 | I | ELDORA Ass Sci (Bell) | 29 | bar: August S 16 to August F 29; September S 7 to September S 21
1 | I | ELDORA Ass Sci (Weckwerth) | 20 | bar: August W 27 to September M 15
2 | I | ELDORA Data Mgmt (Cai) | 37 | bar: August W 6 to August T 21; September S 13 to October F 3
1 | I | ELDORA Data Mgmt (Wolff) | 25 | bar: August F 15 to September M 8
T-PARC / Driftsonde
1 | L | Engineer (Hock) | 36 | bar: August S 9 to September S 13
1 | L | Engineer (Fox) | 36 | bar: August S 9 to September S 13
1 | L | Engineer (Cole) | 22 | bar: August T 12 to September T 2
1 | L | Engineer (Lauritsen) | 31 | bar: August T 28 to September S 27
1 | L | SE (Romberg) | 31 | bar: August T 28 to September S 27
1 | I | Boulder Technical support (24/7) | 42 | bar: August F 15 to September T 25
|  |  | Salary and in-field support base-funded | August S 16: TRIPS:
|  |  | Salary - base funded; In-field support by DP | August S 16: 31 Trips DP - all Guam
|  |  | Salary and in field support covered by DP | August S 16: 4 trips to Monterey
|  |  | Salary base funded, in field support requires special funds | August S 16: 6 trips to Hawaii
|  |  | Salary and in field support requires special funds | August S 16: 2trips to Antarctica
4 trips to Boulder (2 domestic, 2 international)